## PSU-Capstone Drone
Project Plan and Milestones
1 | Investigations and Research Phase
| - Research commercial Drones with Payload Factor | 4 weeks | JAN | Every 1 week Checkpoint |  | Any Out of Sync Meetings will be possible Sat/Sun of every Week. Please Request this in Advance 2-3 days before the weekend.
| - Off the Shelf SW and HW possible |  |  |  | FRIDAY 5pm-6pm
-Excel Calculator and SW sims Testbench
2 | Execution Phase
| -Documentation Starts | 10 weeks | FEB-APR | Every 2 weeks Checkpoint
| - SW Testing |  |  |  | FRIDAY 5pm-6pm
-Metrics for testing and demo
3 | Final Analysis and Reports
| - Algorithms and Results | 4 weeks | APR-MAY | Every 2 weeks Checkpoint
| -Data Driven Conclusions and Next Steps |  |  |  | FRIDAY 5pm-6pm
| BUFFER - for any last minute needs | 2 weeks | MAY
| CAPSTONE finals presentation | 2 weeks | JUNE
TEAM - Please go ahead and come up with a Micro-Schedule(Week by Week) and Roles and Responsibilities among the team members. Would like to review it as soon as possible.
Typical Role Assignments would be :-
Project Management, Organization and Reports, Excel Calc
SW Skilled Member
Overall HW definition skilled member
Testbench Setup and Demo
Analytical study of Drones for Fighting Fires